## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Kaza Venkata Hareesh | 2026-09-02 | Gemini API returned a 429 RESOURCE_EXHAUSTED error while processing an expense analysis request because the free-tier request quota was exceeded. | Sprint 1 | Kaza Venkata Hareesh | Logical | Investigated the error and identified that it was caused by the Gemini API quota limit rather than an application code issue. | 2026-09-02 | Closed | CLI successfully collected the expense details, but AI analysis could not be completed because the Gemini API quota was exhausted.
2 | Kaza Venkata Hareesh | 2026-09-19 | The Receipt Validation Tool was invoked twice during a single expense audit because it was both directly executed and registered as a Gemini-callable tool. | Sprint 2 | Kaza Venkata Hareesh | Logical | Removed validate_receipt from the Gemini registered tools list while retaining direct execution of receipt validation in the expense audit workflow. | 19-09-20226 | Closed | The subsequent CLI test showed one direct receipt validation and successful policy retrieval. The duplicate invocation was resolved in the observed run.
3 | Kaza Venkata Hareesh | 2026-09-19 | During an expense audit with a zero receipt amount, the Receipt Validation Tool correctly flagged the invalid amount, but the AI audit did not complete. | Sprint 2 | Kaza Venkata Hareesh | Logical | Confirmed that the Receipt Validation Tool correctly detected the invalid amount. Further investigation into the subsequent AI service failure is pending, along with a successful end-to-end rerun. | 2026-09-19 | Open | Receipt validation behavior was confirmed, but the complete AI audit remains unverified due to a subsequent service/API failure. Retesting is required after investigating the failure.
4 | Kaza Venkata Hareesh | 2026-09-28 | Specialized agent failure in Coordinator workflow (e.g. PolicyAgent exception) previously caused downstream workflow failure instead of isolated error handling and transparent error reporting. | Sprint 3 | Kaza Venkata Hareesh | Logical | Added try-except blocks around each specialized agent invocation in CoordinatorAgent.run_audit(). Recorded individual agent status ('Failed' vs 'Completed') and formatted user-friendly error strings passed downstream without crashing the pipeline. | 2026-09-29 | Closed | Verified via automated unit test test_agent_failure in tests/test_m3_workflow.py. Policy status set to 'Failed', remaining workflow completed gracefully.
5 | Kaza Venkata Hareesh | 2026-09-29 | Follow-up chat queries using CoordinatorAgent.handle_follow_up() failed with unhandled exception when invoked with an invalid or expired session_id. | Sprint 3 | Kaza Venkata Hareesh | Logical | Added explicit check in handle_follow_up() to query SESSION_STORE.get(session_id). If missing, immediately returns 'No active session context found. Please submit an expense first.' before invoking LLM. | 2026-09-30 | Closed | Verified via automated unit test test_missing_context in tests/test_m3_workflow.py. Returned exact user-friendly message instantly.
6 | Kaza Venkata Hareesh | 2026-10-01 | Gemini API 429 RESOURCE_EXHAUSTED rate-limit errors during follow-up chat conversations exposed technical error messages and raw status codes to the user interface. | Sprint 3 | Kaza Venkata Hareesh | Logical | Added handling in CoordinatorAgent.handle_follow_up() to catch 429/quota exceptions via get_user_friendly_error(), return the user-friendly fallback message 'The AI service has temporarily reached its usage limit. Please try again later.', and preserve the existing SESSION_STORE context. Scope: handle_follow_up() path only. Error handling in run_audit() and the web application layer has not been separately re-tested against live 429 responses in Milestone 3. | 2026-10-02 | Closed | Fix verified by mocked automated unit test test_gemini_429_quota_exhaustion_in_chat in tests/test_m3_workflow.py. Verified behaviours: 429 exception intercepted, raw error message suppressed, session data preserved. Coverage is limited to the handle_follow_up() code path and mocked exception; live API quota exhaustion and other routes remain unverified.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others